## RutaCrítica
E-Commerce Web Site "Led It"
FASE | ACTIVITIES | MONTH/DATE
|  | MAY | [17 empty] | JUNE | [29 empty] | JULY | [30 empty] | AUGUST
|  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2
Planning | bar: MAY 14 to MAY 21
Initial record | bar: MAY 14
Project | bar: MAY 16
Meeting | bar: MAY 17
Lifecycle | bar: MAY 18; MAY 21
Hito of planning | bar: MAY 21
Análisis | bar: MAY 22 to MAY 28
Requirements management | bar: MAY 22 to MAY 25; MAY 28
Identify requirements suppliers | bar: MAY 22
Define data collection techniques | bar: MAY 23
Identify functional requirements | bar: MAY 24
Identify non-functional requirements | bar: MAY 25
Manage requirements traceability | bar: MAY 25; MAY 28
Hito of analysis | bar: MAY 28
Design | bar: MAY 29 to JUNE 13
Diagramas UML | bar: MAY 29 to JUNE 1; JUNE 4 to JUNE 8; JUNE 11 to JUNE 13
Use cases | bar: MAY 29 to MAY 30
Sequence Diagrams | bar: MAY 31 to JUNE 2
Class diagrams | bar: JUNE 4 to JUNE 5
ER diagram | bar: JUNE 6 to JUNE 7
Scketches' design | bar: JUNE 8; JUNE 11 to JUNE 12
Navigation map | bar: JUNE 13
Hito of design | bar: JUNE 13
Development | bar: JUNE 14 to JULY 26
Encode database | bar: JUNE 14 to JUNE 15
Modules | bar: JUNE 18 to JUNE 22; JUNE 25 to JUNE 26
Products | bar: JUNE 18 to JUNE 22
Interface | bar: JUNE 18
Register | bar: JUNE 19
List | bar: JUNE 20
Delete | bar: JUNE 21
Update | bar: JUNE 22
Gallery | bar: JUNE 25 to JUNE 29
Interface | bar: JUNE 25
Register | bar: JUNE 26
List | bar: JUNE 27
Delete | bar: JUNE 28
Update | bar: JUNE 29
Contact | bar: JULY 2 to JULY 5
Interface | bar: JULY 2
Register | bar: JULY 3
List | bar: JULY 4
Delete | bar: JULY 5
FAQ | bar: JULY 6; JULY 9 to JULY 12
Interface | bar: JULY 6
Register | bar: JULY 9
List | bar: JULY 10
Delete | bar: JULY 11
Update | bar: JULY 12
Shopping cart | bar: JULY 13; JULY 16 to JULY 19
Interface | bar: JULY 13
Register | bar: JULY 16
List | bar: JULY 17
Delete | bar: JULY 18
Update | bar: JULY 19
User | bar: JULY 20; JULY 23 to JULY 26
Interface | bar: JULY 20
Register | bar: JULY 23
List | bar: JULY 24
Delete | bar: JULY 25
Update | bar: JULY 26
Hito of development | bar: JULY 26
Implementation | bar: JULY 27
Upload in host | bar: JULY 27
Hito of implementation | bar: JULY 27
Tests | bar: JULY 30 to JULY 31
Testing module | bar: JULY 30
System Tests | bar: JULY 31
Hito of tests | bar: JULY 31
End of project | bar: AUGUST 1 to AUGUST 2
Letter of Acceptance | bar: AUGUST 1
Project closure | bar: AUGUST 2
Performance evaluation | bar: AUGUST 2
Delivery of documentation and presentation | bar: AUGUST 2
Final report | bar: AUGUST 2
Hito of end of project | bar: AUGUST 2
Acotation
No laboral days
End fase hito delivering
Critical path

## WbsNumerado
Sitio Web con Comercio electrónico "Led It"
FASE | Id Actividad | ACTIVITIES | MONTH/DATE
|  |  | MAY | [17 empty] | JUNE | [29 empty] | JULY | [30 empty] | AUGUST
|  |  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2
Planeación | bar: MAY 14 to MAY 21
| Ac-01 | Initial record | bar: MAY 14
| Ac-02 | Project | bar: MAY 16
| Ac-03 | Meeting | bar: MAY 17
| Ac-04 | Lifecycle | bar: MAY 18; MAY 21
Análisis | bar: MAY 22 to MAY 28
Requirements management | bar: MAY 22 to MAY 25; MAY 28
| Ac-05 | Identify requirements suppliers | bar: MAY 22
| Ac-06 | Define data collection techniques | bar: MAY 23
| Ac-07 | Identify functional requirements | bar: MAY 24
| Ac-08 | Identify non-functional requirements | bar: MAY 25
| Ac-09 | Manage requirements traceability | bar: MAY 25; MAY 28
Diseño | bar: MAY 29 to JUNE 13
| Ac-10 | Diagramas UML | bar: MAY 29 to JUNE 1; JUNE 4 to JUNE 8; JUNE 11 to JUNE 13
| Ac-11 | Use cases | bar: MAY 29 to MAY 30
| Ac-12 | Sequence Diagrams | bar: MAY 31 to JUNE 2
| Ac-13 | Class diagrams | bar: JUNE 4 to JUNE 5
| Ac-14 | ER diagram | bar: JUNE 6 to JUNE 7
| Ac-15 | Scketches' design | bar: JUNE 8; JUNE 11 to JUNE 12
| Ac-16 | Navigation map | bar: JUNE 13
Desarrollo - Codificación | bar: JUNE 14 to JULY 26
| Ac-17 | Encode database | bar: JUNE 14 to JUNE 15
| Ac-18 | Modules | bar: JUNE 18 to JUNE 22; JUNE 25 to JUNE 26
| Ac-19 | Products | bar: JUNE 18 to JUNE 22
| Ac-20 | Interface | bar: JUNE 18
| Ac-21 | Register | bar: JUNE 19
| Ac-22 | List | bar: JUNE 20
| Ac-23 | Delete | bar: JUNE 21
| Ac-24 | Update | bar: JUNE 22
| Ac-25 | Gallery | bar: JUNE 25 to JUNE 29
| Ac-26 | Interface | bar: JUNE 25
| Ac-27 | Register | bar: JUNE 26
| Ac-28 | List | bar: JUNE 27
| Ac-29 | Delete | bar: JUNE 28
| Ac-30 | Update | bar: JUNE 29
| Ac-31 | Contact | bar: JULY 2 to JULY 5
| Ac-32 | Interface | bar: JULY 2
| Ac-33 | Register | bar: JULY 3
| Ac-34 | List | bar: JULY 4
| Ac-35 | Delete | bar: JULY 5
| Ac-36 | FAQ | bar: JULY 6; JULY 9 to JULY 12
| Ac-37 | Interface | bar: JULY 6
| Ac-38 | Register | bar: JULY 9
| Ac-39 | List | bar: JULY 10
| Ac-40 | Delete | bar: JULY 11
| Ac-41 | Update | bar: JULY 12
| Ac-42 | Shopping cart | bar: JULY 13; JULY 16 to JULY 19
| Ac-43 | Interface | bar: JULY 13
| Ac-44 | Register | bar: JULY 16
| Ac-45 | List | bar: JULY 17
| Ac-46 | Delete | bar: JULY 18
| Ac-47 | Update | bar: JULY 19
| Ac-48 | User | bar: JULY 20; JULY 23 to JULY 26
| Ac-49 | Interface | bar: JULY 20
| Ac-50 | Register | bar: JULY 23
| Ac-51 | List | bar: JULY 24
| Ac-52 | Delete | bar: JULY 25
| Ac-53 | Update | bar: JULY 26
Implementación | bar: JULY 27
| Ac-54 | Upload in host | bar: JULY 27
Testeo | bar: JULY 30 to JULY 31
| Ac-55 | Testing module | bar: JULY 30
| Ac-56 | System Tests | bar: JULY 31
Fin de proyecto | bar: AUGUST 1 to AUGUST 2
| Ac-57 | Letter of Acceptance | bar: AUGUST 1
| Ac-58 | Project closure | bar: AUGUST 2
| Ac-59 | Performance evaluation | bar: AUGUST 2
| Ac-60 | Delivery of documentation and presentation | bar: AUGUST 2
| Ac-61 | Final report | bar: AUGUST 2
Acotaciones
Días no laborales
Fin de Fase y Entrega de Hito
Ruta Crítica